## Sheet1
Release 1 | Task Points | Task Completed Week 6 | Task Completed Week 7 | Task Completed Week 8 | Task Completed Week 9 | Task Completed Week 10 | Task Completed Week 11 | Task Completed Week 12 | Task Completed Week 13
Story 01: User/Admin Login | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Story 03: User Registration | 7 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Story 04: User/Admin Logout | 5 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Story 05: User Search | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Story 06: Admin Registration | 6 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0
Story 07: Add Information Page | 8 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0
Story 16: Contact Information | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Story 02: User Profile Management | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 08: Add Service Type | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 09: Edit Information Page | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 10: Delete Information Page | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 08: Delete Service Type | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 13: Sort Results | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 15: Upload City Map | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 22: List of available services/areas | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Tasks Remaining | 83 | 80 | 73 | 59 | 54 | 54 | 54 | 54 | 54
Estimated Tasks Remaining | 83 | 72.625 | 62.25 | 51.875 | 41.5 | 31.125 | 20.75 | 10.375 | 0