## Sheet1
Release 1 | Task Points | Task Completed Week 6 | Task Completed Week 7 | Task Completed Week 8 | Task Completed Week 9 | Task Completed Week 10 | Task Completed Week 11 | Task Completed Week 12 | Task Completed Week 13
Story 01: User/Admin Login | 5 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0
Story 03: User Registration | 7 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Story 04: User/Admin Logout | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
Story 05: User Search | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0
Story 06: Admin Registration | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0
Story 07: Add Information Page | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0
Story 16: Contact Information | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Story 28: Google integration | 8 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 3
Story 09: Edit Information Page | 8 | 0 | 0 | 0 | 0 | 2 | 5 | 1 | 0
Story 10: Delete Information Page | 5 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
Story 13: Sort Results | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 15: Upload City Map | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Story 22: List of available services/areas | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Tasks Remaining | 71 | 68 | 61 | 47 | 33 | 24 | 15 | 8 | 5
Estimated Tasks Remaining | 71 | 62.125 | 53.25 | 44.375 | 35.5 | 26.625 | 17.75 | 8.875 | 0
[6 empty] | Sprint 2 | Task Points | Task Completed Week 10 | Task Completed Week 11 | Task Completed Week 12 | Task Completed Week 13
[6 empty] | Story 09: Edit Information Page | 8 | 2 | 5 | 1 | 0
[6 empty] | Story 10: Delete Information Page | 5 | 2 | 3 | 0 | 0
[6 empty] | Story 13: Sort Results | 4 | 0 | 0 | 0 | 0
[6 empty] | Story 28: Google integration | 8 | 2 | 1 | 2 | 3
[6 empty] | Story 15: Upload City Map | 4 | 0 | 0 | 4 | 0
[6 empty] | Story 22: List of available services/areas | 4 | 0 | 0 | 0 | 0
[6 empty] | Story 10: Add Service type | 6 | 0 | 0 | 4 | 2
[6 empty] | Actual Tasks Remaining | 33 | 27 | 18 | 11 | 8
[6 empty] | Estimated Tasks Remaining | 33 | 24.75 | 16.5 | 8.25 | 0